## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Omer Khan | Ruby Rios | Thomas Tran | Sandy Yang | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 5 |  | 125 |  |  |  |  | 18
|  | Research business | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather information (questionnaire) | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Analyze business needs | Requirements Analyst | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Determine what type of tool to use to build website | Requirements Analyst | All | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
|  | Gain access to client WIX account |  | All | 1 |  | 120 | 5 days | 0.25 | 0.25 | 0.25 | 0.25 | 1
| Architecture |  |  |  |  | 2 |  | 2 |  |  |  |  | 2
|  | Designing website layout | Requirements Analyst | All | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
|  | Gather media |  |  | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
| Documentation |  |  |  |  | 7 |  | 5 |  |  |  |  | 5
|  | Project plan | Requirements Analyst | All | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
|  | Milestone / iteration breakdown | Project Manager | All | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
|  | Project documention | Project Manager | All | 2 |  | 2 |  | 0 | 1 | 0 | 1 | 2
|  | User and developer guides | Project Manager | All | 3 |  | 1 |  | 0 | 0.5 | 0 | 0.5 | 1
Design & Build | [8 empty] | 4.25 | 10.75 | 4.25 | 5.75 | 25
Iteration 1: | Development |  |  |  |  | 11.5 |  | 11 |  |  |  |  | 24.4
|  | Research technology needs (SEO for google shopping, website building tool). | Developer | All | 3 |  | 2 |  | 0 | 2 | 0 | 0 | 2
|  | Gain access to the website building tool. | Developer | All | 1 |  | 1 |  | 0 | 1 | 0 | 0 | 1
|  | Contact clients suggesting Wix | Developer | All | 0.5 |  | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Create mock website to show clients | Developer | Ruby Rios | 7 |  | 7 |  | 0 | 7 | 0 | 0 | 7
|  | Update Sitemap. |  | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Update Iteration Est. Effort Spreadsheet |  | All | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Submit files to canvas (Have everyone look everything over first). |  | All | 0.1 |  | 0.1 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.4
| Testing |  |  |  |  | 1 |  | 0.5 |  |  |  |  | 2
|  | Testing e-commerce functionality (mock up) [Will not be testing credit card/paypal with this] | Developer, Quality Assurance | All | 1 |  | 0.5 |  | 0 | 0.5 | 0 | 0 | 0.5
|  | Testing usability and organization on multiple screens (mock up) | Developer, Quality Assurance | All | 1 |  | 0.5 |  | 0 | 0.5 | 0 | 0 | 0.5
|  | Test login functionality (mock up) | Developer, Quality Assurance | All | 1 |  | 0.5 |  | 0 | 0.5 | 0 | 0 | 0.5
|  | Testing social media integration (mock up) | Developer, Quality Assurance | All | 1 |  | 0.5 |  | 0 | 0.5 | 0 | 0 | 0.5
[9 empty] | 7.85 | 26.35 | 7.85 | 9.35 | 51.4
Iteration 2: | Development |  |  |  |  | 25.5 |  | 0 |  |  |  |  | 0
|  | Create a Home page | Developer | Ruby Rios | 2.5 | [7 empty] | 0
|  | Create an "About Us" Page | Developer | Ruby Rios | 1 | [7 empty] | 0
|  | Create a login/account system | Developer | Ruby Rios | 3 | [7 empty] | 0
|  | Insert correct products onto site, using variant pricing | Developer | Ruby Rios | 3 | [7 empty] | 0
|  | Create a "Shipping/Returns Policy" Page | Developer | Ruby Rios | 1 | [7 empty] | 0
|  | Create a "Gallery" Page | Developer | Ruby Rios | 2 | [7 empty] | 0
|  | Create an "Contact Us" Page | Developer | Ruby Rios | 1 | [7 empty] | 0
|  | Create e-commerce related pages | Developer | Ruby Rios | 4 | [7 empty] | 0
|  | Ensure all pages are functional/optimally designed on mobile platforms | Developer | Ruby Rios | 4 | [7 empty] | 0
|  | Insert other integration (collection of emails, chat, etc) | Developer | Ruby Rios | 2 | [7 empty] | 0
|  | Connect social media accounts (facebook, etsy, tik tok). | Developer | Ruby Rios | 2 | [7 empty] | 0
| Testing |  |  |  |  | 2 |  | 0 |  |  |  |  | 0
|  | Retest all functionality on Client's page. Ecommerce, usability, login, and social media integration. | Developer, Quality Assurance | Ruby Rios | 2 | [7 empty] | 0
|  | Testing e-commerce functionality [Now with credit card/paypal] | Developer, Quality Assurance | All | 2 | [7 empty] | 0
|  | Testing usability and organization on multiple screens | Developer, Quality Assurance | All | 1 | [7 empty] | 0
|  | Test login functionality | Developer, Quality Assurance | All | 1 | [7 empty] | 0
|  | Testing social media integration | Developer, Quality Assurance | All | 1 | [7 empty] | 0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
[9 empty] | 7.85 | 26.35 | 7.85 | 9.35 | 51.4
Iteration 3: | [5 empty] | 5 |  | 0 |  |  |  |  | 0
|  | Create user/developer guides | Project Manager | Ruby Rios | 3 | [7 empty] | 0
|  | Complete any additional work from the clients to ensure website is up to their standards | Developer, Quality Assurance | All | 2 | [7 empty] | 0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
Total |  |  |  |  | 70.1 | 59 | 51.4 | 143.5 | 7.85 | 26.35 | 7.85 | 9.35 | 51.4