## Iteration Estimated Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Omer | Ruby | Thomas | Sandy | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 4 |  | 4
|  | Research business | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Gather information (questionnaire) | Requirements Analyst | All | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 4
|  | Analyze business needs | Requirements Analyst | All | 1 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | Determine what type of tool to use to build website | Requirements Analyst | All | 1 | [7 empty] | 0
| Architecture |  |  |  |  | 2 |  | 0 |  |  |  |  | 0
|  | Designing website layout | Requirements Analyst | All | 1 |  |  |  | 0 |  |  |  | 0
|  | Gather media |  |  | 1 |  |  |  | 0 |  |  |  | 0
| Documentation |  |  |  |  | 10 |  | 1 |  |  |  |  | 0
|  | Project plan | Requirements Analyst | All | 1 |  |  |  | 0 |  |  |  | 0
|  | Milestone / iteration breakdown | Project Manager | All | 1 |  | 1 | [5 empty] | 0
|  | Project documention |  | All | 2 | [7 empty] | 0
|  | Project report |  | All | 2 | [7 empty] | 0
|  | Testing report |  | All | 1 | [7 empty] | 0
|  | User and developer guides |  | All | 3 | [7 empty] | 0
Design & Build | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 10.5 |  | 0 |  |  |  |  | 0
|  | Research technology needs (SEO for google shopping, website building tool). | Developer | All | 3 | [7 empty] | 0
|  | Gain access to the website building tool. |  | All | 1 | [7 empty] | 0
|  | Contact clients suggesting Wix |  | All | 0.5 | [7 empty] | 0
|  | Create a Home page | Developer | Thomas Tran | 1
|  | Create an "About Us" Page | Developer | Thomas Tran | 1
|  | Create an "Contact Us" Page | Developer | Omer Khan | 1
|  | Create e-commerce related page | Developer | Sandy Yang | 1
|  | Connect social media accounts (facebook, etsy). | Developer | Ruby Rios | 2 | [7 empty] | 0
| Testing |  |  |  |  | 3 |  | 0 |  |  |  |  | 0
|  | Testing features of future builder (inventory, ecommerce, etc.) | Developer, Quality Assurance | All | 3 | [7 empty] | 0
Iteration 2: | [5 empty] | 0 |  | 0 |  |  |  |  | 0
|  | connect shopping links (etsy) | [10 empty] | 0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
Iteration 3: | [5 empty] | 0 |  | 0 |  |  |  |  | 0
|  | future client userability | [10 empty] | 0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
0
0
0
[6 empty] | 0 |  | 0 |  |  |  |  | 0
0
0
Total |  |  |  |  | 29.5 | 29.5 | 16 | 5 | 4 | 4 | 4 | 4 | 16